## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | TODAYS DATE | 2024-10-01 | TOTAL DAYS | ssum the suratons
| Product Release | Alex B. | 2024-09-02 | 2024-10-10 |  | % finished |  | SCOPE STATEMENT |  | TOTAL FINISHED | Sum if status is FINISHED
Approved | TASK NAME | LOCATION | RESPONSIBLE | # OF MEN | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2024-09-03 | 2024-09-13 | 10
| Feature 1 |  | Frank C. |  | 2024-09-03 | 2024-09-07 | 4
| Feature 2 |  | Jacob S. |  | 2024-09-07 | 2024-09-12 | 5
| Feature 3 |  | Jacob S. |  | 2024-09-09 | 2024-09-13 | 4
| Sprint 2 |  | Jacob S. |  | 2024-09-16 | 2024-09-24 | 8
| Feature 4 |  | Alex B. |  | 2024-09-16 | 2024-09-17 | 1
| Feature 5 |  | Frank C. |  | 2024-09-17 | 2024-09-21 | 4
| Feature 6 |  | Shari W. |  | 2024-09-24 | 2024-09-24 | 0
| Sprint 3 |  | Shari W. |  | 2024-09-25 | 2024-10-05 | 10
| Feature 7 |  | Alex B. |  | 2024-09-25 | 2024-09-29 | 4
| Feature 8 |  | Kennedy K. |  | 2024-09-24 | 2024-10-02 | 8
| Feature 9 |  | Jacob S. |  | 2024-10-02 | 2024-10-05 | 3

## Agile Project Plan (2)
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | TODAYS DATE | 2024-10-01 | TOTAL DAYS | 61
| Product Release | Alex B. | 2024-09-02 | 2024-10-10 |  | 65.57% |  | SCOPE STATEMENT |  | TOTAL FINISHED | 40
Approved | TASK NAME | LOCATION | RESPONSIBLE | # OF MEN | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2024-09-03 | 2024-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2024-09-03 | 2024-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2024-09-07 | 2024-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2024-09-09 | 2024-09-13 | 4 | Complete
| Sprint 2 |  | Jacob S. |  | 2024-09-16 | 2024-09-24 | 8 | Complete
| Feature 4 |  | Alex B. |  | 2024-09-16 | 2024-09-17 | 1 | Complete
| Feature 5 |  | Frank C. |  | 2024-09-17 | 2024-09-21 | 4 | Complete
| Feature 6 |  | Shari W. |  | 2024-09-24 | 2024-09-24 | 0 | Complete
| Sprint 3 |  | Shari W. |  | 2024-09-25 | 2024-10-05 | 10 | in progress
| Feature 7 |  | Alex B. |  | 2024-09-25 | 2024-09-29 | 4 | Complete
| Feature 8 |  | Kennedy K. |  | 2024-09-24 | 2024-10-02 | 8 | in progress
| Feature 9 |  | Jacob S. |  | 2024-10-02 | 2024-10-05 | 3 | not started yet